## Brambleton
CONTRACTOR CONTACT INFO:
[5 empty] | Lump Sum | LS | Weiman Golf Design LLC
[5 empty] | Linear Feet | LF | www.weimangolfdesign.com
[5 empty] | Square Feet | SF | joel@weimangolfdesign.com
[5 empty] | Cubic Yards | CY | 410-365-2080
[5 empty] | Each | EA
[5 empty] | Tons | TN
BID DATE: |  |  |  |  | Allowance | AL
REVISED:
BID SUBMITTAL of Golf Course Improvements
Brambleton Regional Park Golf Course
Northern Virginia Regional Park Authority
[9 empty] | Hole #15 |  | Hole #18
[9 empty] | Right Bunker: 800 SF |  | Right Bunker: 1300 SF
[9 empty] | Left Bunker: 1300 SF |  | Left Bunker: 900 SF
[9 empty] | Widen Right Side Approach |  | Rear Bunker: 600 SF
[9 empty] | NO IRRIGATION |  | NO IRRIGATION
1 | SITE PREPARATION |  | Unit Costs | Units | Quantity | Cost | Quantity | Cost | Quantity | Cost | Quantity | Cost
| a | Mobilization: Fixed Costs | 1 | LS |  | 0 |  | 0 |  | 0 |  | 0
| b | Layout, Staking, and As-Builts | 1 | EA |  | 0 |  | 0 |  | 0 |  | 0
| c | Demo: Cut, Strip, Dispose On-Site of Existing Turf |  | SF |  |  |  |  | 13000 | 0 | 17500 | 0
| d | Demo: Miscellaneous (stairs, etc.) | 1 | LS |  | 0 |  | 0 | 0 | 0 | 0 | 0
| e | Purchase, Install, Maintain, Remove Silt Fence |  | LF |  |  |  |  | 100 | 0 | 100 | 0
| f | Haul Road Protection and Repair AL | 1 | LS |  | 0 |  | 0 |  | 0 |  | 0
2 | EARTHWORK
| a | Topsoil Management: Strip at 4" Depth, Store, Replate |  | CY |  |  |  |  | 115 | 0 | 120 | 0
| b | Remove, Dispose On-Site of Ex. Bunker Sand (estimated 5" depth) |  | TN |  |  |  |  | 56 | 0 | 92 | 0
| c | Excavation: Localized Cut-to-Fill |  | CY |  |  |  |  | 165 | 0 | 145 | 0
| d | Excavation: Hauled Cut/Fill |  | CY |  |  |  |  | 0 | 0 | 75 | 0
| e | Excavate, Flip, Bury Sand Build-Up Bunker Faces, Replate w/Compacted Soil |  | EA |  |  |  |  | 2 | 0 | 3 | 0
| f | Artwork & Contouring (incl. all architectural adjustments) | 1 | LS |  | 0 |  | 0 |  | 0 |  | 0
3 | FEATURE CONSTRUCTION
| a | Install 4" N-12 Solid Drain Pipe |  | LF |  |  |  |  | 130 | 0 | 190 | 0
| b | Install 3'x3'x1.5' Bubble-Up Sump, Drainage Tie-In |  | EA |  |  |  |  | 1 | 0 | 2 | 0
| c | Install 4" N-12 Perforated Pipe w/Gravel Backfill |  | LF |  |  |  |  | 210 | 0 | 280 | 0
| d | Purchase Trench Gravel Material (supplier: xxx) |  | TN |  |  |  |  | 10 | 0 | 13 | 0
| e | Purchase Tee/Trench Mix Material (supplier: xxx) |  | TN |  |  |  |  | 1 | 0 | 0 | 0
| f | Edge, Install Tee Mix at 6" Compacted Depth |  | SF |  |  |  |  | 0 | 0 | 0 | 0
| g | Laser Level Tee Surface |  | SF |  |  |  |  | 0 | 0 | 0 | 0
| h | Irrigation: Purchase & Install Irrigation (1 head & 70 LF of 2" pipe) |  | LS |  |  |  |  | 0 | 0 | 0 | 0
| i | Additional Drainage: Install 12" Drain Inlet |  | EA |  |  |  |  | 0 | 0 | 0 | 0
| j | Purchase Bunker Sand Material (supplier: xxx) |  | TN |  |  |  | 0 | 60 | 0 | 79 | 0
| k | Edge Bunkers, Install Sand at Uniform, Compacted 6" Depth |  | TN |  |  |  | 0 | 60 | 0 | 79 | 0
4 | GRASSING
| a | Approach/Tee: Prepare Soil for Grassing |  | SF |  |  |  |  | 3500 | 0 | 0 | 0
| b | Approach/Tee: Purch. Bentgrass Fairway Sod (supplier: xxx) |  | SF |  |  |  |  | 3500 | 0 | 0 | 0
| c | Approach/Tee: Install Sod |  | SF |  |  |  |  | 3500 | 0 | 0 | 0
| d | Rough Surrounds: Prepare Soil for Grassing |  | SF |  |  |  |  | 9500 | 0 | 16000 | 0
| e | Rough Surrounds: Purchase TTTF Sod (supplier: xxx) |  | SF |  |  |  |  | 9500 | 0 | 16000 | 0
| f | Rough Surrounds: Install Sod (all slopes to be pinned) |  | SF |  |  |  |  | 9500 | 0 | 16000 | 0
[6 empty] | 0 |  | 0 | #15 Bunkers: | 0 | #18 Bunkers: | 0
|  | 0 | :Contractor Labor and Equipment Costs
:Equipment Mobilization Cost
|  | 0 | :Contractor's Total Cost
CONTRACTOR'S NOTES AND CLARIFICATIONS (if any):
1
2
3
4
5
6
7
8
9
10